## Team Members
Team Member | Role
Alice | Project Manager
Bob | Data Scientist
Charlie | AI Engineer
Diana | Automation Expert
Ethan | IoT Specialist

## Projects Overview
Project Name | Resources | Description | Value
Smart Line Monitoring | Alice, Bob | Monitoring production lines in real-time with AI insights | High
Predictive Maintenance | Charlie, Diana | Predictive maintenance system using machine learning | Medium
Energy Optimization | Ethan | Optimization of energy consumption across factories | High
Digital Twin | Alice, Ethan | Creating digital twins of factory equipment | High
Worker Safety AI | Bob, Charlie | AI-based system for worker safety monitoring | Medium

## Smart Line Monitoring
Date | Project | Phase | Status | Notes | Risk | Next Action | Updated By
2025-01-07 | Smart Line Monitoring | Initiation | Completed | Security review required | Medium | Tune model hyperparameters | Ethan
2025-01-13 | Smart Line Monitoring | Requirements | Completed | PO approval received | Low | Security alignment | Charlie
2025-01-20 | Smart Line Monitoring | Design | In Progress | PO approval received | Medium | Fix failing tests | Bob
2025-01-26 | Smart Line Monitoring | Infrastructure Setup | In Progress | Blocked by firewall policy | High | Create roll-out checklist | Bob
2025-02-02 | Smart Line Monitoring | Training | Blocked | Infrastructure issue: VPN access | High | Draft training plan | Charlie
2025-02-07 | Smart Line Monitoring | Data Collection | Completed | Risk registered and mitigations planned | Medium | Draft training plan | Ethan
2025-02-15 | Smart Line Monitoring | UAT | In Progress | Model not converging; tuning required | Low | Tune model hyperparameters | Charlie
2025-02-19 | Smart Line Monitoring | Pilot | On Hold | Green light for next phase | Medium | Draft training plan | Bob
2025-02-26 | Smart Line Monitoring | Model Development | Blocked | License procurement awaiting approval | High | Schedule meeting | Ethan
2025-03-05 | Smart Line Monitoring | Integration | Blocked | Requirements workshop planned | Medium | Procurement follow-up | Alice
2025-03-15 | Smart Line Monitoring | Rollout | At Risk | User feedback incorporated | Low | Tune model hyperparameters | Alice
2025-03-24 | Smart Line Monitoring | Maintenance | On Hold | Blocked by firewall policy | High | Create roll-out checklist | Alice
2025-03-31 | Smart Line Monitoring | Hypercare | Completed | License procurement awaiting approval | High | Fix failing tests | Ethan
2025-04-08 | Smart Line Monitoring | Procurement | Blocked | License procurement awaiting approval | High | Update stakeholders | Charlie
2025-04-13 | Smart Line Monitoring | Initiation | Blocked | Blocked by firewall policy | High | Tune model hyperparameters | Charlie
2025-04-16 | Smart Line Monitoring | Requirements | Not Started | Blocked by firewall policy | Medium | Request access | Charlie
2025-04-21 | Smart Line Monitoring | Design | In Progress | Customer on leave; decisions delayed | Low | Draft training plan | Alice
2025-04-26 | Smart Line Monitoring | Infrastructure Setup | In Progress | PO approval received | High | Fix failing tests | Diana
2025-05-06 | Smart Line Monitoring | Training | Completed | Rollback executed; root-cause under analysis | Low | Schedule meeting | Bob
2025-05-13 | Smart Line Monitoring | Data Collection | At Risk | License procurement awaiting approval | Medium | Tune model hyperparameters | Ethan
2025-05-20 | Smart Line Monitoring | UAT | At Risk | Training materials drafted | Low | Prepare design doc | Bob
2025-05-26 | Smart Line Monitoring | Pilot | On Hold | Training materials drafted | Low | Draft training plan | Bob
2025-05-29 | Smart Line Monitoring | Model Development | At Risk | Vendor dependency delayed | Low | Update stakeholders | Alice
2025-06-06 | Smart Line Monitoring | Integration | Blocked | Vendor dependency delayed | High | Update stakeholders | Alice
2025-06-12 | Smart Line Monitoring | Rollout | Completed | Phase completed successfully | Low | Tune model hyperparameters | Diana
2025-06-16 | Smart Line Monitoring | Maintenance | Completed | Phase completed successfully | Low | Fix failing tests | Alice
2025-06-23 | Smart Line Monitoring | Hypercare | Completed | Phase completed successfully | High | Request access | Diana
2025-06-30 | Smart Line Monitoring | Procurement | On Hold | KPIs defined and baselined | Low | Update stakeholders | Diana
2025-07-05 | Smart Line Monitoring | Initiation | In Progress | Infrastructure issue: VPN access | Low | Schedule meeting | Alice
2025-07-13 | Smart Line Monitoring | Requirements | Blocked | Hardware lead time longer than expected | Low | Tune model hyperparameters | Diana
2025-07-20 | Smart Line Monitoring | Design | In Progress | Security review required | High | Draft training plan | Bob
2025-07-23 | Smart Line Monitoring | Infrastructure Setup | Blocked | Performance below SLA in pilot | Low | Schedule meeting | Diana

## Predictive Maintenance
Date | Project | Phase | Status | Notes | Risk | Next Action | Updated By
2025-01-12 | Predictive Maintenance | Initiation | In Progress | Requirements workshop planned | High | Security alignment | Diana
2025-01-18 | Predictive Maintenance | Requirements | Blocked | Vendor dependency delayed | High | Request access | Diana
2025-01-25 | Predictive Maintenance | Design | In Progress | Risk registered and mitigations planned | Low | Schedule meeting | Diana
2025-01-29 | Predictive Maintenance | Infrastructure Setup | Not Started | Security review required | High | Security alignment | Bob
2025-02-03 | Predictive Maintenance | Training | Blocked | License procurement awaiting approval | High | Tune model hyperparameters | Charlie
2025-02-12 | Predictive Maintenance | Model Development | In Progress | Performance below SLA in pilot | High | Create roll-out checklist | Ethan
2025-02-19 | Predictive Maintenance | Integration | In Progress | Requirements workshop planned | Medium | Update stakeholders | Charlie
2025-02-25 | Predictive Maintenance | Data Collection | At Risk | Requirements workshop planned | High | Draft training plan | Alice
2025-03-03 | Predictive Maintenance | Procurement | In Progress | Stakeholder sign-off pending | Medium | Update stakeholders | Bob
2025-03-07 | Predictive Maintenance | UAT | Blocked | Blocked by firewall policy | Low | Create roll-out checklist | Ethan
2025-03-13 | Predictive Maintenance | Hypercare | Completed | Green light for next phase | Medium | Fix failing tests | Charlie
2025-03-17 | Predictive Maintenance | Rollout | Completed | Vendor dependency delayed | Medium | Tune model hyperparameters | Charlie
2025-03-25 | Predictive Maintenance | Maintenance | In Progress | Vendor dependency delayed | Medium | Update stakeholders | Alice
2025-04-01 | Predictive Maintenance | Pilot | Not Started | Rollback executed; root-cause under analysis | High | Create roll-out checklist | Bob
2025-04-05 | Predictive Maintenance | Initiation | On Hold | Vendor dependency delayed | Medium | Create roll-out checklist | Diana
2025-04-14 | Predictive Maintenance | Requirements | On Hold | Dataset quality concerns identified | High | Prepare design doc | Alice
2025-04-17 | Predictive Maintenance | Design | Completed | Dataset quality concerns identified | Medium | Schedule meeting | Diana
2025-04-23 | Predictive Maintenance | Infrastructure Setup | On Hold | User feedback incorporated | High | Procurement follow-up | Charlie
2025-05-03 | Predictive Maintenance | Training | In Progress | Bug triage completed | High | Fix failing tests | Alice
2025-05-12 | Predictive Maintenance | Model Development | Completed | PO approval received | Medium | Security alignment | Diana
2025-05-18 | Predictive Maintenance | Integration | Blocked | Bug triage completed | High | Procurement follow-up | Charlie
2025-05-21 | Predictive Maintenance | Data Collection | In Progress | Infrastructure issue: VPN access | Low | Procurement follow-up | Charlie
2025-05-28 | Predictive Maintenance | Procurement | In Progress | Rollback executed; root-cause under analysis | Low | Create roll-out checklist | Bob
2025-06-05 | Predictive Maintenance | UAT | Blocked | Blocked by firewall policy | High | Security alignment | Charlie
2025-06-08 | Predictive Maintenance | Hypercare | In Progress | Power outage in test lab | Low | Fix failing tests | Bob
2025-06-16 | Predictive Maintenance | Rollout | In Progress | Rollback executed; root-cause under analysis | High | Prepare design doc | Diana
2025-06-24 | Predictive Maintenance | Maintenance | Completed | PO approval received | Medium | Procurement follow-up | Diana
2025-06-28 | Predictive Maintenance | Pilot | Completed | Phase completed successfully | Medium | Prepare design doc | Charlie
2025-07-07 | Predictive Maintenance | Initiation | Blocked | License procurement awaiting approval | Medium | Fix failing tests | Alice
2025-07-14 | Predictive Maintenance | Requirements | At Risk | PO approval received | High | Request access | Bob
2025-07-20 | Predictive Maintenance | Design | On Hold | Dataset quality concerns identified | High | Schedule meeting | Alice
2025-07-29 | Predictive Maintenance | Infrastructure Setup | Completed | Phase completed successfully | High | Security alignment | Bob

## Energy Optimization
Date | Project | Phase | Status | Notes | Risk | Next Action | Updated By
2025-01-17 | Energy Optimization | Initiation | In Progress | Power outage in test lab | High | Procurement follow-up | Bob
2025-01-21 | Energy Optimization | Requirements | In Progress | Data drift detected in production | Medium | Request access | Bob
2025-01-30 | Energy Optimization | Design | In Progress | PO approval received | Low | Draft training plan | Diana
2025-02-05 | Energy Optimization | Infrastructure Setup | In Progress | Bug triage completed | Medium | Update stakeholders | Alice
2025-02-11 | Energy Optimization | Pilot | Blocked | License procurement awaiting approval | Low | Update stakeholders | Ethan
2025-02-19 | Energy Optimization | Integration | At Risk | User feedback incorporated | Low | Update stakeholders | Alice
2025-02-27 | Energy Optimization | Procurement | Completed | Dataset quality concerns identified | High | Request access | Alice
2025-03-04 | Energy Optimization | Rollout | Completed | Stakeholder sign-off pending | High | Request access | Bob
2025-03-09 | Energy Optimization | Data Collection | In Progress | Dataset quality concerns identified | High | Security alignment | Charlie
2025-03-19 | Energy Optimization | Model Development | On Hold | Performance below SLA in pilot | Low | Request access | Ethan
2025-03-26 | Energy Optimization | Training | Blocked | Customer on leave; decisions delayed | High | Prepare design doc | Charlie
2025-04-05 | Energy Optimization | Maintenance | In Progress | Bug triage completed | Medium | Tune model hyperparameters | Alice
2025-04-15 | Energy Optimization | UAT | At Risk | Risk registered and mitigations planned | Low | Update stakeholders | Charlie
2025-04-18 | Energy Optimization | Hypercare | Blocked | User feedback incorporated | High | Fix failing tests | Bob
2025-04-21 | Energy Optimization | Initiation | In Progress | Model not converging; tuning required | High | Draft training plan | Ethan
2025-04-27 | Energy Optimization | Requirements | At Risk | PO approval received | Medium | Create roll-out checklist | Alice
2025-05-04 | Energy Optimization | Design | At Risk | PO approval received | High | Schedule meeting | Ethan
2025-05-12 | Energy Optimization | Infrastructure Setup | In Progress | Risk registered and mitigations planned | High | Tune model hyperparameters | Ethan
2025-05-20 | Energy Optimization | Pilot | In Progress | Vendor dependency delayed | Medium | Fix failing tests | Bob
2025-05-28 | Energy Optimization | Integration | In Progress | Requirements workshop planned | Medium | Create roll-out checklist | Bob
2025-06-02 | Energy Optimization | Procurement | Completed | Infrastructure issue: VPN access | Medium | Update stakeholders | Diana
2025-06-07 | Energy Optimization | Rollout | In Progress | Stakeholder sign-off pending | Low | Procurement follow-up | Diana
2025-06-14 | Energy Optimization | Data Collection | At Risk | Performance below SLA in pilot | Low | Prepare design doc | Charlie
2025-06-23 | Energy Optimization | Model Development | On Hold | Blocked by firewall policy | Low | Schedule meeting | Charlie
2025-06-30 | Energy Optimization | Training | Blocked | Performance below SLA in pilot | High | Draft training plan | Bob
2025-07-09 | Energy Optimization | Maintenance | Blocked | Performance below SLA in pilot | Low | Create roll-out checklist | Diana
2025-07-16 | Energy Optimization | UAT | Blocked | Blocked by firewall policy | Medium | Fix failing tests | Charlie
2025-07-21 | Energy Optimization | Hypercare | Completed | Phase completed successfully | High | Schedule meeting | Diana
2025-07-30 | Energy Optimization | Initiation | On Hold | PO approval received | Low | Create roll-out checklist | Alice
2025-08-03 | Energy Optimization | Requirements | Completed | Phase completed successfully | High | Create roll-out checklist | Charlie
2025-08-12 | Energy Optimization | Design | Blocked | License procurement awaiting approval | High | Request access | Bob
2025-08-21 | Energy Optimization | Infrastructure Setup | Blocked | Blocked by firewall policy | Low | Procurement follow-up | Bob

## Digital Twin
Date | Project | Phase | Status | Notes | Risk | Next Action | Updated By
2025-01-22 | Digital Twin | Initiation | On Hold | Stakeholder sign-off pending | Low | Prepare design doc | Alice
2025-01-31 | Digital Twin | Requirements | In Progress | Rollback executed; root-cause under analysis | Medium | Fix failing tests | Charlie
2025-02-07 | Digital Twin | Design | In Progress | KPIs defined and baselined | High | Schedule meeting | Ethan
2025-02-15 | Digital Twin | Infrastructure Setup | Completed | Customer on leave; decisions delayed | Medium | Request access | Charlie
2025-02-25 | Digital Twin | Maintenance | Blocked | License procurement awaiting approval | Low | Schedule meeting | Diana
2025-03-06 | Digital Twin | UAT | In Progress | Performance below SLA in pilot | Medium | Update stakeholders | Ethan
2025-03-14 | Digital Twin | Model Development | Completed | Security review required | Medium | Procurement follow-up | Bob
2025-03-22 | Digital Twin | Data Collection | Blocked | User feedback incorporated | High | Procurement follow-up | Bob
2025-03-30 | Digital Twin | Rollout | Not Started | Change request received | Low | Create roll-out checklist | Diana
2025-04-02 | Digital Twin | Pilot | On Hold | License procurement awaiting approval | Medium | Procurement follow-up | Diana
2025-04-11 | Digital Twin | Integration | In Progress | KPIs defined and baselined | High | Update stakeholders | Charlie
2025-04-15 | Digital Twin | Hypercare | In Progress | Requirements workshop planned | High | Schedule meeting | Ethan
2025-04-24 | Digital Twin | Training | On Hold | Change request received | Medium | Prepare design doc | Ethan
2025-05-01 | Digital Twin | Procurement | On Hold | Rollback executed; root-cause under analysis | High | Request access | Diana
2025-05-08 | Digital Twin | Initiation | In Progress | KPIs defined and baselined | High | Draft training plan | Bob
2025-05-17 | Digital Twin | Requirements | At Risk | Dataset quality concerns identified | High | Procurement follow-up | Diana
2025-05-20 | Digital Twin | Design | Completed | Stakeholder sign-off pending | Medium | Fix failing tests | Bob
2025-05-27 | Digital Twin | Infrastructure Setup | Not Started | License procurement awaiting approval | Medium | Procurement follow-up | Alice
2025-06-04 | Digital Twin | Maintenance | In Progress | Training materials drafted | Low | Tune model hyperparameters | Diana
2025-06-12 | Digital Twin | UAT | In Progress | Power outage in test lab | Medium | Tune model hyperparameters | Ethan
2025-06-17 | Digital Twin | Model Development | In Progress | Integration tests failing intermittently | Low | Update stakeholders | Ethan
2025-06-26 | Digital Twin | Data Collection | In Progress | Bug triage completed | Low | Request access | Ethan
2025-07-03 | Digital Twin | Rollout | Blocked | Infrastructure issue: VPN access | Low | Request access | Diana
2025-07-10 | Digital Twin | Pilot | Blocked | Vendor dependency delayed | High | Prepare design doc | Charlie
2025-07-19 | Digital Twin | Integration | In Progress | Power outage in test lab | Medium | Schedule meeting | Alice
2025-07-25 | Digital Twin | Hypercare | Blocked | Performance below SLA in pilot | Low | Tune model hyperparameters | Charlie
2025-08-01 | Digital Twin | Training | At Risk | Requirements workshop planned | Medium | Draft training plan | Ethan
2025-08-05 | Digital Twin | Procurement | At Risk | PO approval received | High | Update stakeholders | Ethan
2025-08-13 | Digital Twin | Initiation | In Progress | Dataset quality concerns identified | Medium | Update stakeholders | Charlie
2025-08-23 | Digital Twin | Requirements | In Progress | Requirements workshop planned | Medium | Draft training plan | Alice
2025-08-28 | Digital Twin | Design | In Progress | Rollback executed; root-cause under analysis | Medium | Procurement follow-up | Alice
2025-09-01 | Digital Twin | Infrastructure Setup | Completed | Phase completed successfully | High | Procurement follow-up | Charlie

## Worker Safety AI
Date | Project | Phase | Status | Notes | Risk | Next Action | Updated By
2025-01-27 | Worker Safety AI | Initiation | In Progress | Green light for next phase | Low | Security alignment | Charlie
2025-01-30 | Worker Safety AI | Requirements | Not Started | Rollback executed; root-cause under analysis | Medium | Security alignment | Alice
2025-02-03 | Worker Safety AI | Design | In Progress | Risk registered and mitigations planned | Low | Security alignment | Charlie
2025-02-12 | Worker Safety AI | Infrastructure Setup | In Progress | Vendor dependency delayed | High | Fix failing tests | Charlie
2025-02-18 | Worker Safety AI | Rollout | Blocked | Security review required | High | Tune model hyperparameters | Diana
2025-02-21 | Worker Safety AI | Hypercare | Blocked | License procurement awaiting approval | High | Procurement follow-up | Ethan
2025-02-25 | Worker Safety AI | Model Development | In Progress | Performance below SLA in pilot | High | Draft training plan | Diana
2025-02-28 | Worker Safety AI | Maintenance | Blocked | PO approval received | Low | Draft training plan | Alice
2025-03-03 | Worker Safety AI | Integration | Not Started | Rollback executed; root-cause under analysis | Medium | Update stakeholders | Diana
2025-03-08 | Worker Safety AI | Procurement | In Progress | Bug triage completed | Medium | Prepare design doc | Alice
2025-03-13 | Worker Safety AI | UAT | In Progress | KPIs defined and baselined | Low | Draft training plan | Charlie
2025-03-19 | Worker Safety AI | Pilot | In Progress | User feedback incorporated | Low | Tune model hyperparameters | Charlie
2025-03-26 | Worker Safety AI | Data Collection | Completed | PO approval received | Medium | Tune model hyperparameters | Charlie
2025-04-04 | Worker Safety AI | Training | In Progress | Infrastructure issue: VPN access | Medium | Schedule meeting | Ethan
2025-04-09 | Worker Safety AI | Initiation | In Progress | Performance below SLA in pilot | Low | Procurement follow-up | Diana
2025-04-18 | Worker Safety AI | Requirements | Blocked | Infrastructure issue: VPN access | Low | Tune model hyperparameters | Charlie
2025-04-24 | Worker Safety AI | Design | Blocked | Infrastructure issue: VPN access | High | Create roll-out checklist | Charlie
2025-04-28 | Worker Safety AI | Infrastructure Setup | Not Started | Bug triage completed | High | Create roll-out checklist | Alice
2025-05-08 | Worker Safety AI | Rollout | At Risk | Green light for next phase | Low | Draft training plan | Charlie
2025-05-12 | Worker Safety AI | Hypercare | Completed | Change request received | Low | Security alignment | Charlie
2025-05-20 | Worker Safety AI | Model Development | Not Started | Stakeholder sign-off pending | Medium | Fix failing tests | Alice
2025-05-27 | Worker Safety AI | Maintenance | Completed | Requirements workshop planned | Medium | Create roll-out checklist | Charlie
2025-06-04 | Worker Safety AI | Integration | In Progress | Vendor dependency delayed | Low | Fix failing tests | Bob
2025-06-11 | Worker Safety AI | Procurement | Completed | Requirements workshop planned | Low | Procurement follow-up | Bob
2025-06-20 | Worker Safety AI | UAT | Completed | Phase completed successfully | High | Update stakeholders | Charlie
2025-06-29 | Worker Safety AI | Pilot | In Progress | Blocked by firewall policy | Low | Procurement follow-up | Alice
2025-07-09 | Worker Safety AI | Data Collection | At Risk | Vendor dependency delayed | High | Procurement follow-up | Ethan
2025-07-17 | Worker Safety AI | Training | Completed | Phase completed successfully | Low | Security alignment | Charlie
2025-07-23 | Worker Safety AI | Initiation | On Hold | Green light for next phase | High | Tune model hyperparameters | Charlie
2025-07-31 | Worker Safety AI | Requirements | At Risk | Security review required | Medium | Tune model hyperparameters | Ethan
2025-08-08 | Worker Safety AI | Design | Completed | Phase completed successfully | Low | Prepare design doc | Charlie
2025-08-15 | Worker Safety AI | Infrastructure Setup | Completed | Phase completed successfully | High | Request access | Charlie